## Slide 1
Cross-Channel Support Hub Roadmap
Q3 2012
Q2 2012
Q4 2012
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Wave 1
Content Analysis and Process Framework
Goals:
Develop Support doc review workflow process
Complete portal inventory
Prioritize future portal content
Manage audience/access
Conduct needs analysis with SME Content Contributors
Develop framework and training outlines for SME Content Contributors
Update portal navigation
Post Best Practices
Wave 2
Wave 3
Content Collaboration, Standards and Training
Goals:
Create standard prereq training for SME Content Contributors
Establish formal agreement/project plans for posting content
Create editing checklists and quick references
Create search tips ref
Incorporate search and usage reporting into future content development
Establish template guidelines
Evaluate User Engagement, Increase Content Offerings
Goals:
Create Support Hub tour
Evaluate/improve content dev/review workflow
Establish formal feedback system
Identify SME owners for Community forums
Develop Community forum workflow
Evaluate content links and cross-references
Establish 2013 UX goals

## Slide 2
Cross-Channel Support Hub Roadmap
Q2 2012 – Progress Update
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Goals
Content Analysis and Process Framework
Develop Support doc review workflow process
Complete portal inventory
Prioritize future portal content
Manage audience/access
Conduct needs analysis with SME Content Contributors (Client Eng, Rel Readiness)
Develop framework and training outlines for SME Content Contributors
Update portal navigation
Post Best Practices
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Content Analysis and Process Framework
Support Doc draft and review process: over 40 topics added or updated
Developed draft process and outline for Implementation Ops Guide
Designed initial curriculum for SME Content Contributor training
Updated portal navigation
Posted Best Practices and tutorial cross references to YouTube channel.
Created “living” content inventory document
Results
More
Requested URL redirect via crosschannelsupporthub.com
Contributed to marketing’s Usage & Style Guide
Assisted with onboarding technical writer, John Douglass
Clarified official support portal name (Cross-Channel Support Hub)
Researched strategy/workaround to manage MindTouch user notifications (future notifications will be branded as ClickSquared)
Researched video hosting options to make “long” (>15 mins) videos available
Attended multiple product training sessions

## Slide 3
Cross-Channel Support Hub Roadmap
Q3 2012 – Progress Update
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Goals
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Content Collaboration, Standards and Training
Refined Support Doc draft process
Developed onboarding plan for tech writer
Completed initial analysis for SME Content Contributor training
Added separate playlist for clickSOCIAL promo videos
Successfully transitioned Release Notes development process to Product Owner
Updated checklists and references
Updated home page image icons
Create Release Notes templates
Results
More
Recommended enterprise video hosting solution
Created support demo for summit user conference
Developing image library for single-sourcing
Documented process for updating user guide topics
Launched successful test of email campaign to increase support portal awareness
Contributed to sample FaceBook pages for clickSOCIAL training
Revised FAQs
27% increase in content contributor roles (authors, editors, admins)
17% increase in users (new logins)
48% of all content edited during Q3
Content Collaboration, Standards and Training
Goals:
Create standard prereq training for SME Content Contributors
Establish formal agreement/project plans for posting content
Create editing checklists and quick references
Create search tips ref
Incorporate search and usage reporting into future content development
Establish template guidelines

## Slide 4
Cross-Channel Support Hub Roadmap
Q4 2012 – Progress Update
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Goals
Major Themes:
Ease of use, new GUI
Drag & drop design
Centralized libraries
Ad-hoc data exploration & visual selection
Integrated analytics (historical & predictive)
Cross-channel execution & contact history
Performance improvements
Presented Support Hub lunch and learn overview
Implemented staging area to improve content development/review workflow.
Implemented user survey to request Support Hub feedback.
Launched discussion board for internal Community forum.
Launched Product Management pages and created sample knowledge base page for known issues (pre-release) awareness.
Submitted recommendations for embedded user assistance.
Results
More
Migrated video content to new video hosting solution (with related branding and updated links)
Consistent delivery of Support Hub Insider newsletter (biweekly internally, transitioning to monthly).
Launched client-facing version of Support Hub Insider newsletter.
Supported testing of several training improvements including post-course assessments.
Implemented Google Analytics to gather additional usage/tracking data.
Executed plan to make Release Notes customer-facing.
Evaluate User Engagement, Increase Content Offerings
Goals:
Create Support Hub tour
Evaluate/improve content dev/review workflow
Establish formal feedback system
Identify SME owners for Community forums
Develop Community forum workflow
Evaluate content links and cross-references
Establish 2013 UX goals